## Sheet1
RE: | Dependencies | Description | Motivation | Release | Duration
FR1 |  | Install Game | This requirement makes the game available to the players | 1
FR2 | FR1 | Logo/Loading Screen | This masks the load time. | 1
FR3 | FR1, FR2 | Load Game Scripts | Allow for the game scripts to load to have the game become playable | 1
FR4 | FR1, FR2, FR3 | Main Menu Screen | Requirement to give the interactable main menu screen | 1
FR5 | FR1, FR2, FR3, FR4 | Options Screen | Can view and use the options screen | 1
FR6 | FR1, FR2, FR3, FR4, FR5 | Change Resolution | Option to change resolution and have it affect the game | 2
FR7 | FR1, FR2, FR3, FR4, FR5 | Adjust Graphics Quality | Swap graphics quality based on computer performance | 2
FR8 | FR1, FR2, FR3, FR4 | Start Game | Requirement to allow the start of the playable game | 1
FR9 | FR1, FR2, FR3, FR4, FR5 | Select Brightness Level | Ability to adjust overall game brightness from option screen | 2
FR10 | FR1, FR2, FR3, FR4 | View Control Scheme | View display of controls from option screen | 2
FR11 | FR1, FR2, FR3, FR4 | View Game Credits | Can view the game's credits from option screen | 2
FR12 | FR1, FR2, FR3, FR4 | Exit Game | Give ability to exit the current game | 1
FR13 | FR1, FR2, FR3, FR4, FR8 | Load Playable Island Object | Requirement to load the island object | 1
FR14 | FR1, FR2, FR3, FR4, FR8, FR13 | Attach Enemy Spawn Points | After island is loaded, we will need to place the enemies in their location | 2
FR15 | FR1, FR2, FR3, FR4, FR8, FR13 | Begin Game Music & Audio | The game audio should begin to play for the player | 1
FR16 | FR1, FR2, FR3, FR4, FR8, FR13 | Load Day/Night Cycle & Lighting | The game should change from day to night and vice versa | 1
FR17 | FR1, FR2, FR3, FR4, FR8, FR13 | Initialize Treasure Chest | On the island, the treasure chest should load and appear to the player | 2
FR18 | FR1, FR2, FR3, FR4, FR8, FR13 | Load Player Model | The player model assets should be loading in the background | 1
FR19 | FR1, FR2, FR3, FR4, FR8, FR13, FR18 | Generate Player Character | The player model should load on the screen | 1
FR20 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19 | Attach Control Scheme to Player Character | The control schemes should be attached to the player object | 1
FR21 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19 | Load Sword & Shield | The sword and shield assets should load and be applied to the character | 2
FR22 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19, FR20 | Player Movement | This requirement will let the user move the character | 1
FR23 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19, FR20 | Player Jumping | This requirement allows for the user to jump up into the air | 1
FR24 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19, FR20 | Player Attacking | This will allow the user to make attacks and deal damage to an enemy source | 2
FR25 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19, FR20 | Player Blocking | This will allow the user to block damage from incoming attacks | 2
FR26 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19, FR20 | Player Health Regeneration by Potion Drinking | The user will be able to drink potions to regain health | 2
FR27 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19, FR20 | Player Death | The player will die when his health reaches zero and will be removed from the game | 2
FR28 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19, FR20, FR22 | Player Essence Collection | The player will be able to collect essences from the downed enemy character | 2
FR29 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19, FR20 | Player Climbing | This requirement allows the player to climb up ladders in the game | 2
FR30 | FR1, FR2, FR3, FR4, FR8, FR13, FR14 | Generate Enemy Characters | This requirement will spawn the enemy characters on the island | 2
FR31 | FR1, FR2, FR3, FR4, FR8, FR13, FR14, FR30 | Place Enemies in Spawn Points | When the island is loaded, the enemies will be spawned at their desired location | 2
FR32 | FR1, FR2, FR3, FR4, FR8, FR13, FR14, FR18, FR19, FR20, FR22, FR30, FR31 | Enemy Combat Triggered | Enemy combat will be triggered when the player comes within range | 2
FR33 | FR1, FR2, FR3, FR4, FR8, FR13, FR14, FR18, FR19, FR20, FR22, FR30, FR31 | Enemy Combat Deactivated | The enemy combat will be deactivated when the player leaves the range | 2
FR34 | FR1, FR2, FR3, FR4, FR8, FR13, FR14, FR30, FR31 | Enemy Basic Attack | The enemy will be able to make a basic attack | 2
FR35 | FR1, FR2, FR3, FR4, FR8, FR13, FR14, FR30, FR31 | Enemy Special Attack | The enemy can now make a special attack | 2
FR36 | FR1, FR2, FR3, FR4, FR8, FR13, FR14, FR18, FR19, FR20, FR22, FR24, FR30, FR31 | Enemy Death | This requirement allows the enemy to die when its health reaches zero | 2
FR37 | FR1, FR2, FR3, FR4, FR8, FR13, FR14, FR30, FR31, FR36 | Enemy Drops Essence | The enemy will drop essences when they die | 2
FR38 | FR1, FR2, FR3, FR4, FR8, FR13 | Generate Non-Playable Character | This requirement will allow the non-player character to appear on the island | 2
FR39 | FR1, FR2, FR3, FR4, FR8, FR13 | Non-Playable Character Dialogue | The non-player character will be able to interacted with | 2
FR40 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19 | Generate Heads-Up-Display | The heads-up display will show up to the player | 1
FR41 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19, FR40 | Character Health & Stamina Bar | The character's health and stamina will be displayed on screen and will grow/shrink in real-time | 1
FR42 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19 | Currently Equipped Items | The display for the currently equipped items will appear on screen | 2
FR43 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19 | Current Amount of Collected Essences | This requirement will show the current amount of collected essences to the player | 2
FR44 | FR1, FR2, FR3, FR4, FR8, FR13, FR18, FR19 | Current Amount of Available Potions | The current amount of potions will show up on screen | 2
FR45 | FR1, FR2, FR3, FR4, FR5, FR8, FR13 | Pause Game and In-Game Menu | The player will be able to stop the gameplay and bring up the pause game menu | 1